## Slide 1: Implementing Career Resources, Service-Delivery Tools, and Services
From “Designing and Implementing Career Programs: A Handbook for Effective Practice”
James P. Sampson, Jr.
Copyright 2008
National Career Development Association

## Slide 2: Organization of the Presentation
<number>
Assumptions about Implementation
Eight-Step Implementation Model

## Slide 3: Assumptions about Implementation
<number>
Correcting a problem takes longer than the time invested in planning that might have prevented the problem
Some planning is better than no planning at all
Implementation is an ongoing process that can improve over time

## Slide 4: Eight-Step Implementation Model

## Slide 5: Intended Outcomes of Using the Model
<number>
Help staff to make best use of the limited time that is available for evaluation and planning
Help staff to better anticipate, and then potentially avoid, typical problems in changing career resources, service delivery tools, and services

## Slide 6
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 7: Evaluate Current Career Resources, Service Delivery Tools, and Services
<number>
Prepare for evaluation
Assess needs
Evaluate current career resources, service delivery tools, and services
Prepare for implementation
Communicate with staff and stakeholders

## Slide 8
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 9: Select, Adapt, Revise, & Develop Improved Resources, Service Delivery Tools, & Services
<number>
Prepare for enhancing career resources, service delivery tools, and services
Improve career resources, service delivery tools, and services
Plan and use a formative evaluation of resources, service delivery tools, and services

## Slide 10: Select, Adapt, Revise, & Develop Improved Resources, Service Delivery Tools, & Services
<number>
Explore opportunities for collaboration with other organizations
Communicate with staff and stakeholders

## Slide 11
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 12: Integrate Improved & Existing Resources, Service Delivery Tools, & Services
<number>
Prepare for integrating career resources, service delivery tools, and services
Integrate new and existing career resources, service delivery tools, and services
Plan strategies for summative evaluation and accountability

## Slide 13: Integrate Improved & Existing Resources, Service Delivery Tools, & Services
<number>
Evaluate the progress in integrating career resources, service delivery tools, and services
Plan the specific delivery of career resources, service delivery tools, and services at pilot sites
Prepare to market career resources and services to the public
Communicate with staff and stakeholders

## Slide 14
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 15: Train Staff Members Involved in Pilot Testing
<number>
Plan training for staff in pilot sites
Provide training for staff in pilot sites
Conduct a formative evaluation of pilot staff training
Communicate with staff and stakeholders

## Slide 16
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Conduct Pilot Testing
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 17: Conduct Pilot Testing
<number>
Conduct the first pilot test and an optional second pilot test
Evaluate the progress in pilot testing
Prepare to market career resources and services to the public
Communicate with staff and stakeholders

## Slide 18
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Conduct Pilot Testing
Train All Staff
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 19: Train All Staff Members
<number>
Revise the plan for staff training as needed
Conduct staff training
Market career resources and services to the public
Communicate with staff and stakeholders

## Slide 20
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Conduct Pilot Testing
Train All Staff
Deliver Career Resources and Services
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 21: Deliver Career Resources & Services
<number>
Deliver career resources and services in career centers and schools
Communicate with staff and stakeholders
Market career resources and services to the public

## Slide 22
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Conduct Pilot Testing
Train All Staff
Deliver Career Resources and Services
Complete Evaluation and Accountability
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 23: Conduct Ongoing Evaluation and Establish Accountability
<number>
Collect, analyze, and interpret evaluation data
Collect, describe, and disseminate accountability data
Communicate with staff and stakeholders

## Slide 24
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Conduct Pilot Testing
Train All Staff
Deliver Career Resources and Services
Complete Evaluation and Accountability
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 25
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Conduct Pilot Testing
Train All Staff
Deliver Career Resources and Services
Complete Evaluation and Accountability
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 26
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Conduct Pilot Testing
Train All Staff
Deliver Career Resources and Services
Complete Evaluation and Accountability
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 27
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Conduct Pilot Testing
Train All Staff
Deliver Career Resources and Services
Complete Evaluation and Accountability
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 28: Complete Eight-Step Implementation Model

## Slide 29
Select, Revise, and Develop Improved Career Resources, Service Delivery Tools, and Services
Integrate Improved Career Resources, Service Delivery Tools, and Services with Existing Career Resources, Service Delivery Tools, and Services
Conduct Pilot Testing
Train All Staff
Deliver Career Resources and Services
Complete Evaluation and Accountability
Train Staff in Pilot Career Centers & Schools
Evaluate Current Career Resources, Service Delivery Tools, and Services

## Slide 30: Reference
<number>
Sampson, J. P., Jr. (2008). Designing and implementing career programs: A handbook for effective practice. Broken Arrow, OK: National Career Development Association.

## Slide 31: For more information
www.career.fsu.edu/techcenter